# MISSION: 10,000 Emails + 10,000 Phone Numbers

| Owner | Zak + Zach |
| --- | --- |
| Timeline | 60 days post-brand launch (Weeks 4-12) |
| Budget | $21,000 from initial $50K |
| Status | Brand assets arriving in 2-3 weeks |

## PHASE 1: PREP (Weeks 1-3)

Do this while waiting for brand assets. Zero ad spend.

### Week 1-2: Foundation

- Finalize content strategy and shot list

- Set up TikTok business account (@drinkshroome)

- Set up Instagram business account (@drinkshroome)

- Claim YouTube channel

- Set up Pinterest business account

- Register for TikTok Shop seller account

- Create link-in-bio page pointing to drinkshroome.com

- Research and DM 100 micro-influencers (5K-50K followers)

- Build influencer outreach spreadsheet

- Join Reddit: r/matcha, r/supplements, r/nootropics

- Identify 10 wellness newsletter partners

- Draft 20 TikTok video concepts

- Draft 10 Instagram Reel concepts

### Week 3: Brand Assets Arrive

- Update website with new branding (Brand Asset Refresh SOP)

- Create content templates for social

- Shoot founder content (talking head, product demos)

- Create 5-10 UGC-style videos for organic + ads

- Design ad creative (3-5 static + 3-5 video)

- Set up Meta Business Suite + Pixel

- Set up TikTok Ads Manager + Pixel

- Install both pixels on drinkshroome.com

## PHASE 2: ORGANIC BLITZ (Weeks 4-5)

$0 spend. Prove messaging before paid.

### Daily Actions

- Post 1-2x on TikTok

- Post 1x on Instagram (Reel or carousel)

- Engage 30 min/day: comment on 20 posts, reply to every DM

- Post 1x in Reddit threads (value-first)

### Content Themes

| Day | Theme | Example |
| --- | --- | --- |
| Mon | Product education | most supplements have 15% beta-glucans. ours has 70%+ |
| Tue | Lifestyle | my 30-second morning ritual |
| Wed | Transparency | what is in every sachet |
| Thu | Founder story | why we started shroome |
| Fri | Social proof | X people on the waitlist |
| Sat | Fun/trending | trending sounds, duets |
| Sun | Community | Q&A, polls |

### Targets

| Metric | Week 4 | Week 5 |
| --- | --- | --- |
| TikTok posts | 10-14 | 10-14 |
| Instagram posts | 5-7 | 5-7 |
| New email signups | 300-500 | 500-800 |
| New phone signups | 100-200 | 200-350 |

## PHASE 3: PAID + INFLUENCER (Weeks 6-9)

$15,000 budget over 4 weeks.

| Channel | Total | Signups | Cost/Signup |
| --- | --- | --- | --- |
| TikTok Ads | $6,000 | 2,500 | $2.40 |
| Meta Ads | $4,000 | 1,500 | $2.67 |
| Influencer Seeding | $3,000 | 1,500 | $2.00 |
| Referral Program | $1,000 | 800 | $1.25 |
| Email Partnerships | $1,000 | 500 | $2.00 |
| TOTAL | $15,000 | 6,800 | $2.21 |

### Weekly Tracking

| Week | Email | Phone | Cum. Email | Cum. Phone |
| --- | --- | --- | --- | --- |
| 6 | 1,200 | 500 | 2,000 | 750 |
| 7 | 1,800 | 800 | 3,800 | 1,550 |
| 8 | 2,200 | 1,000 | 6,000 | 2,550 |
| 9 | 2,500 | 1,200 | 8,500 | 3,750 |

## PHASE 4: FINAL PUSH (Weeks 10-12)

$6,000 remaining budget.

- Giveaway ($1,000): Win a year supply - requires email + phone

- Scale winning ads ($3,000): Double best performers

- Countdown urgency: Waitlist closes in X days

- Influencer round 2 ($1,000): 15 more kits

- Cross-promotion ($1,000): 2-3 complementary brands

### Phone Acceleration Tactics

- Make phone the default CTA - ask first

- Add incentive: 24-hour early access for phone subscribers

- SMS-exclusive behind-the-scenes content

- TikTok content about the phone benefit

- Giveaway requires phone entry

- Referral bonus for phone

## BUDGET SUMMARY

| Phase | Timing | Budget | Signups |
| --- | --- | --- | --- |
| Prep | Wk 1-3 | $0 | Foundation |
| Organic | Wk 4-5 | $0 | ~1,000 email / ~400 phone |
| Paid+Influencer | Wk 6-9 | $15,000 | 6,800 email / 3,200 phone |
| Final Push | Wk 10-12 | $6,000 | 7,000 email / 6,250 phone |
| TOTAL | 12 weeks | $21,000 | ~15,000 email / ~10,000 phone |

## DAILY OPERATOR CHECKLIST

Every morning (15 min):

- Check overnight signups (Klaviyo)

- Check ad performance (kill/scale)

- Reply to all DMs and comments

Every afternoon (30 min):

- Post 1 TikTok

- Post 1 Instagram story or reel

- Engage: comment on 10 posts

- Check Google Sheets

Every Friday (1 hour):

- Weekly metrics review

- Adjust ad budgets

- Plan next week content

- Influencer follow-ups

## RISKS AND CONTINGENCIES

| Risk | Likelihood | Contingency |
| --- | --- | --- |
| TikTok ads underperform | MEDIUM | Shift to Meta + influencers |
| Phone opt-in rate low | HIGH | Increase incentive, phone first |
| Content not viral | MEDIUM | More hooks, educational angles |
| Influencer posts flop | LOW | Seed more kits |
| Budget runs out | LOW | Pause ads, go organic |
| CAC exceeds $5 | MEDIUM | Pause paid, partnerships |

## WHAT SUCCESS LOOKS LIKE

By the end of 12 weeks:

- 10,000+ email subscribers on Klaviyo

- 10,000+ phone subscribers on Klaviyo SMS

- 5K+ TikTok followers

- Proven content hooks ready for launch

- Influencer relationships for launch day

- Retargeting audiences on Meta + TikTok

- Email + SMS flows optimized

- Ready to launch